## Plan
K-Merge Phase 3: work left for full proof
How to use: fill in the yellow cells (Actual GPU hours, Result / notes, Done?). Blue numbers are planned estimates; "under 1 h" is counted as 1 h. Totals are on the Summary sheet, pass rules on the Pass rules sheet.
Example of a filled row (example only, not a real result): Actual GPU hours = 4.6 · Result / notes = "Seed 2 done; split still ahead of K-Merge and RegMean (Holm p < 0.05)" · Done? = Yes
# | Part | Item | What it proves / why | GPU hours (planned) | GPU time as stated | Status (5 Oct 2026) | When | Pass rule | Actual GPU hours | Result / notes | Done?
1 | 1. Full proof | Crowded-slot test, seeds 1 and 2 | K-Share beating split when all 12 tasks share a 4-direction slot (94.4% vs 87.1%) wasn't luck from one seed | 5 | ~5 h | Ready to run | Week 1 | K-Share beats split at 4 directions on all 3 seeds |  |  | No
2 | 1. Full proof | Real benchmark, seed 2 | The main result (split 98.9% vs K-Merge 90.8%) holds on 3 seeds, not just 2 | 4.5 | ~4.5 h | Ready to run | Week 1 | Split beats K-Merge and RegMean with p < 0.05 on 3 seeds, at K = 2 and K = 4 |  |  | No
3 | 1. Full proof | K-Share with exactly equal storage, real data | K-Share's win doesn't come from its 2–8% extra storage | 1 | under 1 h | Small change | Week 1 | Equal-storage K-Share stays within about 1 point of normal K-Share |  |  | No
4 | 1. Full proof | KnOTS baseline, real data | Sharing also beats the strongest merging method reviewers will ask about | 1 | under 1 h | Code exists in the lab | Week 2 | Sharing also beats KnOTS on the real tasks |  |  | No
5 | 1. Full proof | Strictly online sharing, real data | Sharing still works when the phone keeps only the slot and never the original adapters, which is K-Merge's real setting. So far this is only tested in the lab. | 1 | ~1 h (my estimate) | Lab code exists; needs moving to the real benchmark | Week 1 | Online sharing stays within about 1–2 points of the rebuilt version |  |  | No
6 | 1. Full proof | Llama-3.2-1B, the K-Merge paper's other model | The result isn't specific to Qwen | 5 | ~5 h | Small code change | Week 2 | Same order on Llama: sharing first, then the best merge, then K-Merge |  |  | No
7 | 2. Open items | Analysis 4 on 3 seeds | The French recovery (0.860 → 0.944) is still from seed 0 only | 1 | ~1 h | Not started | Week 2 | — |  |  | No
8 | 2. Open items | Phase 1 checks (professor's items 20–21) | The seed-0 DE-EN rows and the per-seed similarity scores | 0 | no GPU | Not started | Now | — |  |  | No
9 | 2. Open items | English re-score with official ERRANT (optional) | Uses the saved outputs; answers "your grammar metric only approximates ERRANT" | 0 | no GPU | Optional; not started | Now | — |  |  | No
10 | 3. Own method | Rebuild the K-Share+ code, then GPU pilot | The draft was lost when the old workspace reset. Test it without GPU first (start now), then run the GPU pilot. This could become our own method. | 1 | ~1 h | Draft lost; needs rebuilding | Week 1 | — |  |  | No
11 | 4. Paper | Phone cost: memory and rebuild time | Supports the on-device claim; measured on a computer or a phone | 0 | no GPU | Not started | Weeks 3–4 | — |  |  | No
12 | 4. Paper | Real Hindi grammar data | Blocked until the authors of a Hindi corpus share their data; an ask for the professor | 0 | — | Blocked: waiting for data | Blocked | — |  |  | No
13 | 4. Paper | Add results to the shared Google Doc | The professor's request; needs edit access from her | 0 | — | Waiting for edit access | Weeks 3–4 | — |  |  | No
14 | 4. Paper | Paper draft | Write it after items 1–6 | 0 | — | After items 1–6 | Weeks 3–4 | — |  |  | No
Note on E6: Planned GPU hours from the Phase 3 report's 'What is left' table; item 5 is an estimate. 'under 1 h' is entered as 1 h (upper bound).

## Summary
Summary (updates as you fill in the Plan sheet)
Planned GPU hours, all items | 19.5
Planned GPU hours, Part 1 (full proof, items 1–6) | 17.5
Planned GPU hours still to do (Done? is not Yes) | 19.5
Actual GPU hours used so far | 0
Items done | 0
Items in total | 14
Kaggle free GPU quota per week (hours) | 30
Weeks of quota needed for the GPU work still to do | 0.65
Plan spreads the GPU work over two weeks to leave room for reruns.
By week
When | Planned GPU hours | Items
Now | 0 | 2
Week 1 | 12.5 | 5
Week 2 | 7 | 3
Weeks 3–4 | 0 | 3
Blocked | 0 | 1
Total | 19.5 | 14
Check: total by week equals the Plan total | OK
Note on B9: Kaggle's free quota as stated in our report (30 GPU hours a week). Change it if your quota differs.

## Pass rules
Pass rules: when a claim counts as proved
Write the result next to each rule after the runs. If one rule fails, drop only that claim; the others stand on their own. "Where we are now" is from the Phase 3 report (5 October 2026).
# | Claim to prove | Pass rule (fixed before running) | Experiment | Where we are now | Result (fill in) | Passed?
1 | Main result: sharing beats merging on real tasks | Split beats K-Merge and RegMean with p < 0.05 on 3 seeds, at K = 2 and K = 4 | Item 2 | 2 seeds: split 98.9%, RegMean 95.6%, K-Merge 90.8% (K = 2); all differences p < 0.001 (Holm) |  | Pending
2 | Not specific to Qwen | On Llama-3.2-1B, same order: sharing first, then the best merge, then K-Merge | Item 6 | Not run yet |  | Pending
3 | K-Share's win is not from extra storage | Equal-storage K-Share stays within about 1 point of normal K-Share | Item 3 | K-Share 98.9% using 7.9% extra storage (K = 2); split 98.9% at exactly equal storage |  | Pending
4 | Works in K-Merge's real (online) setting | Online sharing stays within about 1–2 points of the rebuilt version | Item 5 | Tested only in the synthetic lab; real-data slots were rebuilt from the original adapters |  | Pending
5 | Crowded slots need a shared basis | K-Share beats split at 4 directions on all 3 seeds | Item 1 | 1 seed: K-Share 94.4% vs split 87.1% (+7.3 points, 95% CI +5.2 to +9.2) |  | Pending
6 | Beats the strongest merge reviewers will ask about | Sharing also beats KnOTS on the real tasks | Item 4 | KnOTS not run on real data yet |  | Pending
Rules passed |  | 0 of 6